## Sheet1
Module 1: Request for Foreign Travel Authority - Official and personal travel
| EXISTING WORK SCOPE | DETAILS | Estimate (days) | STATUS | REMARKS | Taker
1 | Observe consistency of terminologies | (i.e. Category = Foreign/Local; Type of Travel = Official/Personal; Nature of Travel = Personal; Meetings, Conference etc. | 4 hours | Started
2 | Observe uniformity of terms: | -Scholarship Applications; -Foreign Travel Applications; -Local Travel Applications; | 2 hours
3 | Graphical Report - Requestor's Dashboard | Remove the GR for Travel Request per Sector | 30 minutes
| ADDITIONAL WORK SCOPE | DETAILS | Estimate (days) | STATUS | REMARKS
1 | Reference Code Format |  | 10 working days | Not Started | A reference code was already in placed. | PJ
2 | Add 2 columns after Category: | (1) Type of Travel (i.e. Official/Personal); (2) Nature of Travel (i.e. Personal; Meetings, Conference, Training etc.) |  | Not Started | Adding columns is doable but it will reduce the sizes of the columns thus will compressed all columns in the view section
3 | Additional “Ageing Status” Column | *Ageing Status is determined by the number of days that passed upon receipt of the request. This is to know how many days an action officer act on a specific request. |  | Not Started
4 | Additional Fields in the Graphical Report - Requestor's Dashboard | 1. Travel Request in Central Office (Per Service/Unit); 2. Travel Request Per Agency;
5 | One Reference Code for a Multiple entries for multiple cases | one or multiple a)traveller with b) multiple purpose with c)multiple sector d) multiple destination with e) 1 day or more than 2 days interval with f) one or separate resolution (TA) |  |  | Very complicated logic on the technical side because every categories have different documentary requirements, with corresponding status contents and email triggers; Further, Per reference code in the database are treated per person's travel record. We suggest to retain the single entry process to make it simplier.
6 | Additional Gender Option | Gender: Options: Male, Female, Prefer not to say
7 | Additional Civil Status Option | Civil Status Options: Single, Separated, Widow, Divorced
8 | Gender Equality, Disability, and Social Inclusion (GEDSI) Option | How would you like us to assist you? Please answer truthfully. 1) Do you have mobility problem such as difficulty in walking and/or climbing stairs? 2) Are you having an emotional/behavioural problem? 3) Do you have difficulty in reading and identifying speech sounds? 4) Do you have difficulty communicating? 5) Do you have difficulty remembering or concentrating? 6) Do you have difficulty in doing simple arithmetic calculations? 7) Do you have difficulty reading even with corrective lenses? 8) Do you have any difficulty in hearing? Ethnicity 9) Are you part of the Indigenous People group? 10) Please specify what Ethnic group you belong (e.g. Kapampangan, Cebuano, Bicolano) 11) Are you a solo parent?
9 | Additional "Other Requirements" option to all documentary requirements attachments of all Request for Travel Authority | for cases when HRDD requires additional documentary requirements to be attached.
10 | Add Evaluation Results column after History | Complete, Lack documents, Wrong attachment, With Pending Administrative Case, With Unliquidated Cash Advance, With Pending Post Travel Report |  |  | Can we just modify the contents of the status column. May we suggest instead to be transparent on the status column wherein the particular action will be reflected in the Status column. Else, kindly provide us an updated corresponsing preffered contents per status from the Requestor's dashboard connecting to the Action Officer's dashboard (columns: status, history page, email trigger, Evaluation Results). We need to re-adjust every contents of every column since every action are interconnected with other key functions;
11 | Additional Follow-up button | A notification will pop in the Action Officer’s page once clicked.
12 | Additional upload buton | To require requestor to upload a signed Justification for his request cancellation.
13 | Additional Take Button on Action Column on the Action's Officer Dashboard | Action Officer can take request in the Action Column |  |  | The New Submission Page was created for proper sorting of incoming New Request (travel/scholarship), the Action Officer can just easily click the New Submissions icon located at the top section to take on new request request . Adding an additional Take button and combining new request with previous approved/cancelled/pending requests in the All Action Officer's Dashboard section will mix all entries in the said section. (attached is a canned demo of a section containing all kinds of request without proper sorting)
14 | Additional Email Triggers: To Requestor's email | 1. OTHER ISSUES (IE. UNLIQUIDATED, PENDING CASE, NO PTR) 2. UNSIGNED ATTACHMENT 3. WRONG REQUIREMENT/ATTACHMENT |  |  | Please provide and update the corresponding content of the History column, Evalution column, Status column of the Requestor and Action Officer Dashboard and its corresponding dropdown content when an action officer updates a request.
15 | Additional Email Triggers: To Action Officer's Dashboard | 1. Request Follow-up |  |  | Please provide and update the corresponding content of the History column, Evalution column, Status column of the Requestor and Action Officer Dashboard and its corresponding dropdown content when an action officer updates a request.