## timeline 1.1 (2)
TIMELINE
Module 1 | September 22 to 25, 2020
Database Schema
Admin Console
Login Page
Requestor's Section Home Page
Request for Foreign Travel
Official Travel Request for International Commitment subpage
Official Travel Request for Meetings/ Conferences/ Special Missions subpage
Official Travel Request for Trainings/ Scholarship/ Seminars/ Workshops subpage
Official Travel Request for Factory Acceptance Test/ Inspection other related training subpage
Personal Travel Request subpage
DOTr Central Office - User's Section Page
Official Travel Request for International Commitment subpage
Official Travel Request for Meetings/ Conferences/ Special Missions subpage
Official Travel Request for Trainings/ Scholarship/ Seminars/ Workshops subpage
Official Travel Request for Factory Acceptance Test/ Inspection other related training subpage
Personal Travel Request subpage
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 4 | October 19 to November 9, 2020
Foreign and Local Travel Request Tracker Page
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 5 | November 10 to December 7, 2020
HRDD Action Officer Section Page
Foreign Travel subpage
Local Travel Page subpage
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 6 | December 8 to January 6, 2020
Reports Sub Page
ATMS Menu and link at the DOTr Website
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 7 | January 7 to 9, 2020
System Wide Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 8 | January 9 to February 8, 2020
Preparation of Operational Manual
Maintenance Plan
User's Training
Project Launch/ Deployment | 2020-02-09

## timeline 1.1
TIMELINE
SPRINT 1 | September 3 to 18, 2020
Database Schema
Admin Console
Login Page
User's Section Home Page
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 2 | September 21 to October 6, 2020
Sectoral Offices and Attached Agencies - Action Officer Section
Official Travel Request for International Commitment subpage
Official Travel Request for Meetings/ Conferences/ Special Missions subpage
Official Travel Request for Trainings/ Scholarship/ Seminars/ Workshops subpage
Official Travel Request for Factory Acceptance Test/ Inspection other related training subpage
Personal Travel Request subpage
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 3 | October 7 to 16, 2020
DOTr Central Office - User's Section Page
Official Travel Request for International Commitment subpage
Official Travel Request for Meetings/ Conferences/ Special Missions subpage
Official Travel Request for Trainings/ Scholarship/ Seminars/ Workshops subpage
Official Travel Request for Factory Acceptance Test/ Inspection other related training subpage
Personal Travel Request subpage
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 4 | October 19 to November 9, 2020
Foreign and Local Travel Request Tracker Page
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 5 | November 10 to December 7, 2020
HRDD Action Officer Section Page
Foreign Travel subpage
Local Travel Page subpage
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 6 | December 8 to January 6, 2020
Reports Sub Page
ATMS Menu and link at the DOTr Website
System Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 7 | January 7 to 9, 2020
System Wide Test
Client's Feedback
Adjustment
Release/Deployment
SPRINT 8 | January 9 to February 8, 2020
Preparation of Operational Manual
Maintenance Plan
User's Training
Project Launch/ Deployment | 2020-02-09